## Sheet1
Date Added | Risk ID | Risk Description | Project Stage | Project Category | Risk Owner | Likelihood (1-10) (pre-mitigation) | Impact (1-10) (pre-mitigation) | Risk Priority (pre-mitigation) | Mitigating Action | Likelihood (1-10) (post-mitigation) | Impact (1-10) (post-mitigation) | Risk Priority (post-mitigation)
24-Mar-26 | R1 | I am ready to proceed. Please provide the raw input text containing the 'Risk Description' you would like me to summarize. | Design | Unknown | Unknown | 8 | 8 | High | Mitigating Action:
24-Mar-26 | R4.6 | Data sharing from BBSRI at risk. | Design | Regulations | Environmental | 3 | 3 | Low | Facilitate conversations with Umaine on data sharing
24-Mar-26 | R5 | Ice data collection may be unsuccessful. | Operational | Stakeholder | UAA lead | 2 | 2 | Low | real time data collection implemented
24-Mar-26 | R4 | FERC license not granted in time, risking schedule slip and budget creep. | Pre-construction | Regulations | Environmental | 4 | 4 | Low | Initiate communication with Regulatory agencies and FERC to scope FERC License. Resource appropriately for completion by 12/17, respond to Additional Information Requests promptly after submission
24-Mar-26 | R7 | Wet Gap Generator design not yet complete. | Design | Technical | Lead engineer | 3 | 3 | Low | Design reviews and component validation testing before design finalized
24-Mar-26 | R7 | Tight generator procurement timing risks project schedule. | Assembly and commissioning | Procurement | Lead engineer | 3 | 3 | Low | Ensure Generator delivery by 2/2018 to allow adequate time for testing using project development plan with regular status reports
24-Mar-26 | R7 | Unexpected component shortage may delay buoyancy system validation tests. | Unknown | Procurement | Lead engineer | 3 | 3 | Low | Compile BOM and ascertain component lead times from vendors in advance of PO issue
24-Mar-26 | R7 | Fabricated components have significant lead times. | Unknown | Commercial | Lead engineer | 2 | 6 | Low | Frequent vendor communication, issue PO with room for schedule creep, rapid change order resolution, contractual penalties for schedule slip
24-Mar-26 | R7 | Fabricated components have significant lead times, risking project schedule. | Pre-construction | Procurement | Lead engineer | 2 | 6 | Low | Frequent vendor communication, issue PO with room for schedule creep, rapid change order resolution, contractual penalties for schedule slip
24-Mar-26 | R7 | Single-source vendor dependency risks design completion and fabrication delays. | Pre-construction | Procurement | Project Manager | 3 | 9 | Med | Frequent vendor communication, issue PO with room for schedule creep, rapid change order resolution, contractual penalties for schedule slip
24-Mar-26 | R7 | Unexpected component shortages or personnel shortages for SCADA development may delay integration and system validation. | Unknown | Procurement | Lead engineer | 3 | 3 | Low | Compile BOM and ascertain component lead times from vendors in advance of PO issue
24-Mar-26 | R7 | Fabrication delays and out-of-spec delivered product from suppliers. | Pre-construction | Commercial | Project Manager | 3 | 3 | Low | Compile BOM and ascertain component lead times from vendors in advance of PO issue
24-Mar-26 | R7 | Unexpected component shortage may delay mooring system validation tests. | Pre-construction | Procurement | Lead engineer | 3 | 3 | Low | Compile BOM and ascertain component lead times from vendors in advance of PO issue
24-Mar-26 | R7 | Custom components require fabrication lead time. | Pre-construction | Procurement | Lead engineer | 3 | 2 | Low | Frequent vendor communication, issue PO with room for schedule creep, rapid change order resolution, contractual penalties for schedule slip or incorrect product delivery
24-Mar-26 | R7 | Custom components require fabrication lead time, risking project schedule and budget. | Pre-construction | Procurement | Lead engineer | 3 | 2 | Low | Frequent vendor communication, issue PO with room for schedule creep, rapid change order resolution, contractual penalties for schedule slip or incorrect product delivery
24-Mar-26 | R7 | Buoyancy system fails validation tests, risking project schedule and requiring redesign. | Assembly and commissioning | Technical | Lead engineer | 3 | 6 | Low | Utilizing incremental improvements to a proven concept, add redundancy to design. Perform land based tests in May 2017 and move on to on water validation tests prior to shipment to Igiugig.
24-Mar-26 | R7 | Structural assembly may fail validation tests, risking project integrity and costs. | Assembly and commissioning | Technical | Lead engineer | 2 | 6 | Low | FEA analysis following DNV standards, detailed CAD validation, and incorporate structural redundancy.
24-Mar-26 | R7 | Turbine assembly may fail validation tests, leading to unexpected failure or reduced performance. | Assembly and commissioning | Technical | Lead engineer | 2 | 6 | Low | Utilize CFD as design tool for performance validation, FEA analysis of turbines include load factors following DNV standards and considers extreme loading conditions, secondary design input from composite manufacturer
24-Mar-26 | R7 | Generator fails validation tests, risking project schedule and costs. | Design | Technical | Lead engineer | 2 | 6 | Low | Factory Acceptance testing and laboratory testing of Generator integrated with Power electronics to ensure compatibility before assembly and commissioning
24-Mar-26 | R7 | Power Electronics fails validation, risking project schedule and costs. | Assembly and commissioning | Technical | Project Manager | 3 | 9 | Med | Factory acceptance tests and sequenced laboratory testing to ensure Power Electronics meets requirements before shipment
24-Mar-26 | R7 | SCADA system fails validation. | Assembly and commissioning | Technical | Lead engineer | 3 | 3 | Low | Factory acceptance tests and sequenced laboratory testing to ensure SCADA meets requirements before shipment
24-Mar-26 | R7 | Unexpected power and data cable failure. | Assembly and commissioning | Technical | Project Manager | 4 | 8 | Med | Utilize proven cable technology, secondary cable armor in high risk areas, redundant conductors for data and fiber optic, reduce inspections and associated wear and tear
24-Mar-26 | R7 | Mooring system failure due to inadequate design or validation. | Assembly and commissioning | Technical | Lead engineer | 2 | 5 | Low | Design to DNV standards, utilize geophysical knowledge and industry expertise to specify mooring system components, consider most favorable failure modes.
24-Mar-26 | R7 | Driveline failure risk requiring validation testing and design for increased tolerances. | Assembly and commissioning | Technical | Lead engineer | 4 | 4 | Low | Thorough validation testing, design for increased tolerances and loads, choose long-life low-maintenance components, increase modularity.
24-Mar-26 | R7 | Mechanical brake failure risk requiring validation and redundant electrical brake. | Assembly and commissioning | Technical | Lead engineer | 3 | 3 | Low | Thorough validation testing including redundant electrical brake
24-Mar-26 | R1 | Delays in receiving FERC pilot licenses or permits compromise project deployment. | Pre-construction | Regulations | Environmental | 3 | 3 | Low | Continue regular dialogue with regulatory agencies after final pilot license and other permit applications, respond to AIRs in timely manner
24-Mar-26 | R7 | Component shipment to Igiugig is delayed due to schedule slip, transportation contractor issues, weather, or other factors. | Assembly and commissioning | Management | Project Manager | 4 | 8 | Med | Track project schedule, align component validation and delivery to port of shipment with shipper schedules, ship components early if possible arrival on first barge of season (June 2018) or second (July 2018) at latest
24-Mar-26 | R7 | Device assembly may be difficult or require modification in Igiugig. | Assembly and commissioning | Technical | Lead engineer | 4 | 8 | Med | Preassemble components prior to shipment; include assembly in validation.
24-Mar-26 | R7 | Power system deployment and commissioning may encounter unexpected difficulties. | Assembly and commissioning | Technical | Project Manager | 2 | 10 | Low | prior device testing and component testing in Nikiksi and elsewhere will reduce unexpected issues with deployment or comissioning. Thewe validation steps completed by May 2018
24-Mar-26 | R1 | Ice accumulation or interaction with device causes power disruption, reduction, or equipment damage. | Operational | Technical | Lead engineer | 3 | 3 | Low | Collection of in river ice data for 2 years prior to deployment feeds engineering and IO&M planning, June 2017- June 2018. On device ice monitoring allows for operational state modification if adverse conditions or interactions occur.
24-Mar-26 | R1 | Adverse salmon smolt interactions during device operation. | Operational | Environmental | Environmental | 4 | 4 | Low | Develop rigorous fish monitoring plan in budget period 2, consult with agencies regularly, operate device only under continuous monitoring during smolt outmigration
24-Mar-26 | R17 | Device removal complicated by technological or environmental factors. | Decommissioning | Technical | Project Manager | 2 | 5 | Low | Buoyancy system includes redundant and isolated retrieval mechanisms, pre-testing in Nikiski to reduce risk of retrieval issues arising.
24-Mar-26 | R3 | Higher cost for maintenance and logistical support required. | Assembly and commissioning | Commercial | Project Manager | 4 | 4 | Low | Developing system requirements with local and 3rd party input, training leads, and structuring contracts with incentives/penalties and FFP.