## Sheet1
Date Added | Risk ID | Risk Description | Project Stage | Project Category | Risk Owner | Likelihood (1-10) (pre-mitigation) | Impact (1-10) (pre-mitigation) | Risk Priority (pre-mitigation) | Mitigating Action | Likelihood (1-10) (post-mitigation) | Impact (1-10) (post-mitigation) | Risk Priority (post-mitigation)
24-Mar-26 | R3 | Failure to discharge planning and listed building conditions. | Pre-construction | Planning | Project Manager | 3 | 2 | Low | Design team and contractor to collate initial pack of information for discharge of conditions
24-Mar-26 | R4 | Planning conditions may increase the project budget. | Pre-construction | Planning | Project Manager | 7 | 5 | Med | Review and manage planning conditions
24-Mar-26 | R10 | Delays or non-conformity in electricity provider works risk project schedule and infrastructure compliance. | Construction | Legislation | Project Manager | 3 | 3 | Low | Orders for electrical services placed by CYC direct
24-Mar-26 | R11 | Delays in Building Control sign-off due to resource constraints. | Construction | Legislation | Project Manager | 3 | 3 | Low | Continue liaison with the Building Control Officer
24-Mar-26 | R12 | Impact of boat companies on delivery and site servicing strategy. | Construction | Planning | Project Manager | 3 | 2 | Low | Legal agreements are in place
24-Mar-26 | R13 | Party wall negotiations and neighbor objections risk project delays. | Pre-construction | Planning | Project Manager | 5 | 6 | Med | Appoint party wall surveyor and progress discussions with neighbours
24-Mar-26 | R14 | Failure to secure a suitable restaurant tenant risks long-term revenue and project costs. | Pre-construction | Procurement | Project Manager | 5 | 8 | Med | Early engagement of agent for potential lettings. Sufficient expressions of interest.
24-Mar-26 | R16 | Increased construction costs due to exchange rate volatility and international market impacts. | Construction | Procurement | Project Manager | 5 | 5 | Med | Tender prices received and under review
24-Mar-26 | R18 | Sub-contractor insolvency impacts the main contractor. | Construction | Procurement | Unknown | 7 | 5 | Med | Contractor financial checks and vetting of subcontractors
24-Mar-26 | R20 | Surveys to determine ground conditions or contamination may require design revisions or on-site remediation. | Pre-construction | Technical | Lead engineer | 2 | 8 | Low | GI survey and desk study completed.
24-Mar-26 | R21 | Active movement identification may require costly remediation. | Pre-construction | Technical | Unknown | 2 | 8 | Low | Ongoing monitoring by ARUP and monitoring specification included within contract documents
24-Mar-26 | R22 | Unidentified archaeology may require further evaluation and cause cost impacts. | Pre-construction | Environmental | Environmental | 3 | 3 | Low | Evaluation of site undertaken
24-Mar-26 | R23 | Additional surveys may be required, impacting project costs. | Pre-construction | Technical | Project Manager | 2 | 1 | Low | Undertake outstanding surveys
24-Mar-26 | R26 | Unrealistic contractor programme submission. | Pre-construction | Procurement | Project Manager | 2 | 5 | Low | Market tested
24-Mar-26 | R27 | Flood levels may delay construction, impacting schedule and costs. | Construction | Environmental | Project Manager | 10 | 8 | High | Review historic flood data and issue to Contractor. Develop contingency plan.
24-Mar-26 | R29 | Delays to the design program impact client and contractor costs and schedule. | Pre-construction | Design | Project Manager | 5 | 5 | Med | Implementation of IRS schedules design deliverables and clear responsibility for design
24-Mar-26 | R31 | Underpinning and piling may resolve existing structural issues but could cause new cracks elsewhere. | Pre-construction | Design | Unknown | 5 | 8 | Med | Detailed dilapidations surveys, crack monitors
24-Mar-26 | R32 | Discovery of structural unknowns may require additional surveys and remediation, increasing costs. | Construction | Design | Unknown | 8 | 7 | High | Undertake early surveys to determine unknowns and allow contingency for remediation, focusing on tower underpinning and South Range.
24-Mar-26 | R35 | Undetected services not identified on surveys and drawings risk program delays, redesign, and cost overruns. | Construction | Services | Lead engineer | 3 | 5 | Low | Utilities surveys plotted; careful excavation on site.
24-Mar-26 | R40 | Refusal of Environment Agency license for river source heat pump causes project delays. | Pre-construction | Environmental | Environmental | 2 | 7 | Low | Provisional consent obtained; continued dialogue required
24-Mar-26 | R41 | Sourcing stone for remediation works may be delayed if the quarry closes, requiring new approvals and impacting the program. | Construction | Procurement | Unknown | 7 | 5 | Med | Investigate alternative quarries; secure approval for alternative stone.
24-Mar-26 | R42 | Structural damage to the tower requiring underpinning repairs. | Construction | Technical | Unknown | 6 | 7 | Med | Bullivants/Arup and Vinci designs to be reviewed; building monitoring systems and locations to be agreed.
24-Mar-26 | R48 | Outstanding building defects create legacy issues and impact tenant satisfaction. | Assembly and commissioning | Quality | Project Manager | 3 | 5 | Low | Use retention to resolve defects within contract
24-Mar-26 | R50 | Non-construction costs may exceed the allocated budget. | Construction | Financial | Project Manager | 8 | 5 | Med | Review non construction costs prior to contract award and during construction
24-Mar-26 | R51 | Incorrect estimation and design errors may lead to construction cost overruns. | Pre-construction | Design | Unknown | 5 | 5 | Med | Risk sits with CYC except CDP items
24-Mar-26 | R56 | Shortage of specialist labour or equipment may require specification changes or bespoke solutions. | Construction | Technical | Project Manager | 5 | 5 | Med | Dialogue with main contractor & supply chain
24-Mar-26 | R61 | Poor coordination with design team interfaces for contractor design portions. | Construction | Design | Project Manager | 3 | 5 | Low | Regular meetings with Vinci and Design Team to discuss CDP interfaces.
24-Mar-26 | R62 | Rights of Light. | Pre-construction | Legislation | Project Manager | 1 | 7 | Low | Title report does not identify any issues
24-Mar-26 | R64 | Poor contractor performance during construction. | Construction | Procurement | Project Manager | 3 | 8 | Med | Contract to be signed to protect client - performance bonds to be obtained.
24-Mar-26 | R66 | Unknown South Range structures may reveal an old basement, disrupting piling plans. | Construction | Design | Unknown | 7 | 5 | Med | Conduct detailed site investigation and geotechnical survey before finalizing piling design.
24-Mar-26 | R67 | Insufficient design detail from specialist packages impacts planning condition approvals. | Pre-construction | Design | Unknown | 5 | 1 | Low | Regular design reviews and interface management
24-Mar-26 | R70 | Failure to satisfy EA requirements risks work stoppage and prohibition. | Pre-construction | Environmental | Environmental | 2 | 8 | Low | Waste management and compliance with the EA to ensure no environmental hazards
24-Mar-26 | R72 | Delays in design due to tenant or operator requirement changes. | Pre-construction | Design | Project Manager | 5 | 5 | Med | Recover cost/time via Agreements for Lease for late or significant changes
24-Mar-26 | R73 | Design changes and unforeseen items risk construction cost overruns. | Construction | Design | Project Manager | 10 | 8 | High | Secure adequate contingency
24-Mar-26 | R75 | Weather delays risk project schedule. | Construction | Unknown | Project Manager | 8 | 5 | Med | Contractor to provide impact and allowances via contract
24-Mar-26 | R76 | Underpinning or crack repairs by third parties may cause new cracks and incur remediation costs. | Construction | Design | Unknown | 3 | 8 | Med | Detailed dilapidations surveys, crack monitors
24-Mar-26 | R77 | Insufficient borehole survey depth impacts piling design, causing time and cost overruns. | Pre-construction | Technical | Lead engineer | 5 | 5 | Med | Additional borehole surveys conducted; findings reviewed and confirmed; piling designs updated accordingly.
24-Mar-26 | R80 | Instability to boundary wall requiring structural works. | Construction | Design | Unknown | 5 | 3 | Low | Assessment of wall structure required - Scope of works to be determined
24-Mar-26 | R81 | Clashes between existing foundations and proposed drainage due to lack of information. | Construction | Technical | Lead engineer | 5 | 3 | Low | Trial holes to understand foundations; conservative drainage design with contingency.
24-Mar-26 | R82 | Potential drainage clash with lift shaft pits may require additional external drainage. | Construction | Technical | Lead engineer | 2 | 5 | Low | Trial hole dug and appears clear; review after north annex demolition.
24-Mar-26 | R83 | Billing omissions or inaccuracies in the BoQ risk time and cost increases. | Pre-construction | Financial | Project Manager | 7 | 8 | High | T&T have carried out reviews of the BoQ
24-Mar-26 | R84 | Additional works beyond contract scope risk cost overruns and schedule delays. | Construction | Financial | Project Manager | 10 | 8 | High | Detailed change management process to be followed.
24-Mar-26 | R85 | Ongoing structural movement due to removed underpinning risks cost and schedule overruns. | Construction | Design | Unknown | 3 | 7 | Med | Monitoring during works
24-Mar-26 | R87 | Design changes due to insufficient development and coordination at tender risk cost overruns and schedule delays. | Pre-construction | Design | Project Manager | 3 | 3 | Low | Coordination managed by design team as priority; design changes to retaining wall instructed and underway.
24-Mar-26 | R88 | Council chamber cooling approval may require design revisions, impacting time and cost. | Unknown | Design | Unknown | 3 | 5 | Low | Design team to coordinate with planning / conservation