## Sheet1
Date Added | Risk ID | Risk Description | Project Stage | Project Category | Risk Owner | Likelihood (1-10) (pre-mitigation) | Impact (1-10) (pre-mitigation) | Risk Priority (pre-mitigation) | Mitigating Action | Likelihood (1-10) (post-mitigation) | Impact (1-10) (post-mitigation) | Risk Priority (post-mitigation)
24-Mar-26 | ICT-001 | Identity and Access Management systems are compromised due to outdated operating systems. | Operational | Technical | IT Manager | 3 | 8 | Med | Implement automated IAM systems and multifactor authentication; update application architecture; implement data encryption; adopt ISO 27001 framework.
24-Mar-26 | R2 | Backup and recovery services are undocumented and untested, with critical systems on outdated infrastructure risking database corruption. | Operational | Technical | Unknown | 9 | 8 | High | Implement automated IAM and MFA, update application architecture, implement data encryption, and adopt ISO 27001 framework.
24-Mar-26 | ICT-003 | Critical systems face outages and cyber intrusions due to outdated infrastructure and lack of disaster recovery. | Operational | Technical | Unknown | 10 | 8 | High | Document and test backup and recovery services; migrate systems to new infrastructure; implement ISO 27001 framework and controls.