## Sheet1
Date Added | Risk ID | Risk Description | Project Stage | Project Category | Risk Owner | Likelihood (1-10) (pre-mitigation) | Impact (1-10) (pre-mitigation) | Risk Priority (pre-mitigation) | Mitigating Action | Likelihood (1-10) (post-mitigation) | Impact (1-10) (post-mitigation) | Risk Priority (post-mitigation)
24-Mar-26 | R1 | Data sharing from BBSRI is at risk due to regulatory issues. | Operational | Unknown | Environmental | 3 | 3 | Low | Facilitate conversations with University of Maine on data sharing. If data is not shared, move on to the next step of conceptual monitoring plan development.
24-Mar-26 | R1 | Data sharing from BBSRI is at risk due to regulatory issues. | Operational | Unknown | Environmental | 8 | 9 | High | Facilitate conversations with University of Maine on data sharing. If data is not shared, move on to the next step of conceptual monitoring plan development.
24-Mar-26 | R1 | Data sharing from BBSRI is at risk due to regulatory issues. | Operational | Unknown | Environmental | 2 | 4 | Low | Facilitate conversations with University of Maine on data sharing. If data is not shared, move on to the next step of conceptual monitoring plan development.
24-Mar-26 | R1 | Data sharing from BBSRI is at risk due to regulatory issues. | Operational | Unknown | Environmental | 3 | 3 | Low | Facilitate conversations with University of Maine on data sharing. If data is not shared, move on to the next step of conceptual monitoring plan development.