## Sheet1
Date Added | Risk ID | Risk Description | Project Stage | Project Category | Risk Owner | Likelihood (1-10) (pre-mitigation) | Impact (1-10) (pre-mitigation) | Risk Priority (pre-mitigation) | Mitigating Action | Likelihood (1-10) (post-mitigation) | Impact (1-10) (post-mitigation) | Risk Priority (post-mitigation)
24-Mar-26 | R1 | Opening of the Moorgate Crossrail station is delayed further. | Construction | Adjoining Owners | Project Manager | 5 | 3 | Low | Regular engagement with Crossrail from now to 2020/2021 to allow for alternative arrangements should there be a delay in delivery. | 3 | 2 | Low
24-Mar-26 | R2 | Slippage in construction start may require finding a new Principal Contractor after the Riney highways contract expires in summer 2022. | Construction | Procurement | Project Manager | 3 | 3 | Low | Initiate internal discussions on contingency plans for transferring work to a new contractor if needed. | 1 | 2 | Low
24-Mar-26 | R3 | Delays to the four developments surrounding the Moorgate Crossrail station delay the final delivery phases of the MCSL project. | Construction | Adjoining Owners | Project Manager | 5 | 7 | Med | Regular engagement with developers from now until the completion of the developments to allow for alternative arrangements and early notification of delays. | 3 | 5 | Low
24-Mar-26 | R4 | Infrastructure and utilities difficulties at the Moorgate junction make it difficult and expensive to design and transform the space while enhancing safety. | Design | Technical | Lead engineer | 6 | 8 | Med | Monitor and evaluate. | 3 | 6 | Low
24-Mar-26 | R5 | Key stakeholder(s) do not endorse design options. | Design | Stakeholder | Project Manager | 5 | 7 | Med | Ensure that the Stakeholder Working Group is suitably engaged and informed to secure endorsement. | 3 | 5 | Low
24-Mar-26 | R6 | Delays or changes to dependency projects like Beech Street and St. Paul's Gyratory could impact project timelines. | Construction | Adjoining Owners | Project Manager | 5 | 7 | Med | Work with internal stakeholders to minimize any impacts should changes arise. | 3 | 5 | Low
24-Mar-26 | R7 | Breakdown in engagement with key stakeholders, such as Islington Council. | Multiple (Or All) Life Phases | Stakeholder | Project Manager | 3 | 7 | Med | Ensure coherent communications with stakeholders at strategic points throughout the project, particularly regarding proposed boundary solutions. | 1 | 5 | Low
24-Mar-26 | R8 | TfL restructure may result in no dedicated scheme sponsor or resource being allocated to progress required TfL approvals. | Pre-construction | Management | Project Manager | 6 | 8 | Med | Officers will seek to establish resources early and maintain close contact to understand the restructure's extent, seeking resource reassurance if needed. | 3 | 6 | Low
24-Mar-26 | R9 | The proposed scheme could negatively impact protected characteristics under the Equalities Act 2010. | Design | Legislation | Project Manager | 2 | 7 | Low | Conduct regular meetings with representative groups and engage the EA Team for design feedback to prepare an EA plan. | 1 | 5 | Low
24-Mar-26 | R10 | Traffic resilience requirements restrict design options for Moorgate junctions. | Design | Design | Lead engineer | 5 | 7 | Med | Ensure appropriate resilience levels are incorporated into Moorgate junction designs at London Wall and Ropemaker Street. | 3 | 5 | Low